## Sheet1
Threat | Description | Likelihood Level | Impact Level | Responsibility | Current Mitigation | Proposed Mitigation | Response
H2 console Inaccessible | The H2 console could become inaccessible, meaning the front end could not communicate with the back end and no data would be displayed on the web application | Low | Medium | H2 Console | A way to access MySQL is currently set up, which I have left as comments. There is a dependency to add whilst removing the dependency referring to the H2 console. We should then set up the connection in the application.properties file | current mitigation | Try to restart the database, if not try accessing MySQL instead
Virtual Machine Instance becomes unaccessible | The webserver is running in a Virtual machine hosted by GCP. If the VM become inaccessible, the website will be completely unaccessible | Medium | High | Google Cloud Platform | NONE | Set a backup VM with another provider such as AWS or Microsoft Azure | Create a new VM on GCP if that is possible, adapt the application. If not, either contact GCP or opt for another provider
"Man-in-the-middle attack" | An attacker could secretly relay and alter the communications between the PC terminal and the VM terminal by having access to the private and public keys. | Low | High | Alessia Mele | There is already a layer of proctection with the public and private keys that can be generated at any time. | Implement Anti-CSRF token, using session and cryptography for the secret key. Implement SameSite Cookies, to disable third party usage, so requests sent from different origin are dismisses | Generate immidiately a new set of public and private keys and contact the administrator
Invalid data in the forms | The user can input data in the wrong database field requirement, resultng in the application to break. | Medium | Medium | Alessia Mele | NONE | Extend the use of field requirement checks for users. | If the data doesn't meet the requirement an error is prompted to the user.
Port 8080 becomes unavailable | This can happen either when several applications are running at the same time, or when a previous version of the application is still blocking port 8080. | High | High | Alessia Mele | NONE | Implement a way to kill a process running on a particular port in the config.yaml file | In this case, the best thing to do is to change the port in the application.properties file, and if this doesn't work, stop the virtual machine and restart it. This might require additional reconfiguration as the external IP might change.
Definition
Likelihood Level | High : the risk is likely to append because the source is technically capable, or the user is likely to make mistake in using the application | Medium: the risk could happen, but controls are in place to mitigate it |  | Low: the risk is unlikely to happened
Impact Level | High : the risk occurrence can seriously lead to site malfunction or inaccessibility | Medium: the risk occurrence doesn't lead to major malfunctions or loss of data |  | Low: consequences of the risk occurrence can be recovered because effective procedure are in place
Risk Tolerance | Tolerate: No further action taken, because the risk's consequences are manageable. | Treat: Action taken to minimise the risk's consequences